## Dashboard
PROJECT REPORTING DASHBOARD
DATE | TOTAL ITERATION | 2 | SPRINT 1 START DATE | ITERATION DURATION | 1.5 days | SPRINT 2 START DATE | Team Size
Note:- To view the Burndown chart for a particular day the next day should be selected in the Sprint Progress dropdown. For viewing the complete Sprint Burndown chart the status should be set to completed in the dropdown

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US01 | Creating a Login page component where user can provide their credentials and login to the webpage. | MUST HAVE | 1 | 1084525 | 3- Completed
1 | 1 | US02 | Creating a registration page component where user can register themselves into the website to avail the services and benefits of WanderLust website. | MUST HAVE | 3 | 1084525 | 3- Completed
1 | 1 | US03 | Both visitor and the registered user must be able to look at the hot deals available .They must also be able to search for packages for a particular destination to explore. | MUST HAVE | 5 | 1084525 | 3- Completed
1 | 1 | US04 | Both visitor and the registered user must be able to view the package details so that they can review the whole package. | MUST HAVE | 2 | 1084525 | 3- Completed
2 | 2 | US05 | A logged in user alone should be able to book a desired package. | MUST HAVE | 8 | 1084525 | 3- Completed
2 | 2 | US06 | A logged in user must be able to view their planned trips. | MUST HAVE | 8 | 1084525 | 3- Completed
2 | 2 | US07 | A logged in user must be able to cancel a particular package. | MUST HAVE | 5 | 1084525 | 3- Completed
2 | 2 | US08 | A logged in user must also be able to logout. | MUST HAVE | 1 | 1084525 | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 27.5 | 19 | 0.5 | 0
SPRINT 1 BACKLOG
US-01 | T1 | configuring the servers and setting up the database | 2020-05-08 | 2020-05-08 | 1084525 | General | 3- Completed | 0.5 | 0.5
| T2 | checking if the login page is working | 2020-05-08 | 2020-05-08 | 1084525 | General | 3- Completed | 0.5 | 0.2
T3
T4
T5
T6
T7
T8
| T1 | creating the registration form. | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.5 | 0.3
| T2 | Adding necessary validations for the input fields | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.75 | 0.6
| T3 | Making a database connection to MongoDB from the server. | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.5 | 0.3
US-02 | T4 | Performing CRUD operation in UserModel in Express and generating the user ID and adding the user into db. | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.75 | 0.5
| T5 | Performing the service side input validations in UserService in Express. | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.5 | 0.3
| T6 | Configuring the routes in express. | 2020-05-08 | 2020-05-08 | 1084525 | Coding | 3- Completed | 0.5 | 0.4
| T7 | Making axios request and checking if the registration is successful or not and displaying the appropriate success and error messages and checking if the register page is working. | 2020-05-08 | 2020-05-08 | 1084525 | Integration | 3- Completed | 0.5 | 0.4
| T1 | Creating a SearchPackage component and converting the entered data to desired case and to make a axios request to the database to search for a particular package. | 2020-05-09 | 2020-05-09 | 1084525 | Integration | 3- Completed | 1 | 1
| T2 | In the server side,Creating connection and setup the destination database and CRUD operation must be to get the details of the particular package must be done on UserModel and validations on UserService. | 2020-05-09 | 2020-05-09 | 1084525 | Coding | 3- Completed | 5 | 4
| T3 | The routes must be configured and appropriate response and error message must be sent back to the front end. | 2020-05-09 | 2020-05-09 | 1084525 | Coding | 3- Completed | 1 | 1
US-03 | T4 | The response must be sent to the searchedPackages component and in case of an error,appropriate error messages must be configured. | 2020-05-09 | 2020-05-10 | 1084525 | Coding | 3- Completed | 1 | 0.5 | 0.5
| T5 | The HotDeals button must be configured and the axios request must be sent to server to get the hotdeals available. | 2020-05-10 | 2020-05-10 | 1084525 | Coding | 3- Completed | 1 | 0.5
| T6 | The server side connections,database setup, crud operations and routing must be done.The response is once again sent to searchedPackages component and appropriate error messages are configured. | 2020-05-11 | 2020-05-11 | 1084525 | Coding | 3- Completed | 6 | 5
| T7 | In the searchedPackages component, the received packages must be iterated over and the details must be displayed in the card with appropriate bootstrap classes. | 2020-05-11 | 2020-05-11 | 1084525 | Integration | 3- Completed | 1 | 1
| T1 | Checking if the overview,iternary and book button is working correctly and understanding the code | 2020-05-11 | 2020-05-11 | 1084525 | Coding | 3- Completed | 2 | 1
| T2 | Calculating the charges without clicking the button | 2020-05-11 | 2020-05-11 | 1084525 | Coding | 1- Not Started | 2
| T3 | Configuring book button in the booking form | 2020-05-11 | 2020-05-11 | 1084525 | Coding | 3- Completed | 0.5 | 0.5
US-04 | T4 | Redirecting the book form by checking if the user is logged in or not. | 2020-05-11 | 2020-05-11 | 1084525 | General | 3- Completed | 2 | 1
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 29 | 23.85 | 0.5 | 0
SPRINT 2 BACKLOG
| T1 | Configuring the book component. | 2020-05-12 | 2020-05-12 | 1084525 | Coding | 3- Completed | 5 | 5
| T2 | Creating the form and performing appropriate validations and cost calculations. | 2020-05-12 | 2020-05-12 | 1084525 | Coding | 3- Completed | 2 | 2
| T3 | On successful validation and Onclick of the book button,axios request must be sent to the server to book the package. | 2020-05-12 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 0.5 | 0.5
US-05 | T4 | Performing server side crud operation. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 3 | 3
| T5 | UserService validation in server side. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 1
| T6 | routing the file in UserRouter.js | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 0.5 | 0.5
| T7 | In the BookingPackage component, appropriate error and success messages musst be added. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 0.5 | 0.25
| T8 | checking if the bookingComponent is working successfully and creating the confirmation page. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 3 | 3
| T1 | configuring the planned trips button and redirecting it | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 0.25
| T2 | creating the card to display the details | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 1
| T3 | Making the axios request to get the details of the bookings and performing the server side crud operations and routing to get the details. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 4 | 3
US-06 | T4 | Displaying the details in the card | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 0.75
| T5 | Checking if the planned trips are displaying properly. | 2020-05-13 | 2020-05-13 | 1084525 | General | 3- Completed | 0.5 | 0.5
T6
T7
US-07 | T1 | creating the cancellation popup. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 2 | 1
| T2 | Making the axios request to cancel the booking | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 0.5
| T3 | Creating the server side crud operations and routers to cancel the particular booking. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 1
| T4 | Checking if the cancellation is working properly. | 2020-05-13 | 2020-05-13 | 1084525 | Coding | 3- Completed | 1 | 0.5
T5
T6
T7
US-08 | T1 | Logging out the user | 2020-05-13 | 2020-05-13 | 1084525 | General | 3- Completed | 0.5 | 0.1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2020-05-08 | 2020-05-11 | 1084525 | Start with US-05 | Trying to calculate the charges without clicking the calculate charges button. | Keep filling the agile sheet. | Continued the coding part without it.
2 | 2 | 2020-05-12 | 2020-05-13 | 1084525 | Complete the agile sheet | Stop the project till whatever you have done. |  | Submitted the project till whatever is done.

## Reference Data
SPRINT I BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual | TEAM VELOCITY CHART
1 | 1 | 27.5 | 19.5
| 2 | 18.33 | 19 | Sprint | Planned | Actual
| 3 | 9.16 | 0.5 | 1 | 27.5 | 19.5
|  |  |  | 2 | 29 | 24.35
SPRINT II BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual
2 | 1 | 29 | 24.35
| 2 | 19.33 | 23.85
| 3 | 9.66 | 0.5
Note on E6: Effort hours pending after day 1 of sprint 1
Note on E7: Effort hours pending after day 2 of sprint 1
Note on H7: Planned hours of effort in Sprint 1
Note on I7: Story points completed in sprint 1
Note on H8: Planned hours of effort in Sprint 2
Note on I8: Story points completed in Sprint 2
Note on E15: Effort hours pending after day 1 of sprint 2
Note on E16: Effort hours pending after day 2 of sprint 2

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US-03 | 2 | 1084525 | How to display both hot deals and packages from a same component. | After searching for a particular package,clicking on hotdeals again displayed the same packages | Made separate components for both of them.
1 | US-03 | 2 | 1084525 | Searching for both continent and destination names in the search bar | The search was searching only for the continents. | Made the names in packages into separate list and added it in the crud operations.
2 | US-05 | 1 | 1084525 | Finding out how to display the package in details in the booking page in the given format. | Figuring out which ui component provides the same pattern. | Prime react fieldset component provides the desired output.
2 | US-07 | 2 | 1084525 | Finding out how to display the popup in cancellation page. | Displaying the popup. | Prime react Dialog Box provides the desired output.

## Product Backlog Grooming
Sprint | US ID | Points Discussed
1 | US-03 | How to find the packages based on continent name as well as the destination name.
1 | US-03 | How to display both hot deals and packages from a same component.
1 | US-04 | How to configure the book button in sidebar so that it checks if the user is logged in or not .
2 | US-05 | How to display the overview,iternary and package inclusions in the toggelable bar
2 | US-05 | How to check if the booking request received is from hotdeals or packages.